## Sheet1
Task Number | Task Name | Duration | Start | Finish | Deliverables | Milestones | Resources
| Inception Planning Stage | 28 Days | 2021-02-01 | 2021-03-01
1 | Receive Initial Brief | 0 Days | 2021-02-01 | 2021-02-01 |  | x | Initial Brief
2 | Analysis of brief | 0 Days | 2021-02-01 | 2021-02-01 |  |  | Initial Brief, Microsoft Word
3 | Submit questions for the client | 14 Days | 2021-02-01 | 2021-02-15 | Questions for Client | x | Microsoft Word
4 | Get client questions feedback | 0 Days | 2021-02-16 | 2021-02-16 |  | x
5 | Complete Project Plan | 1 Day | 2021-02-15 | 2021-02-16 |  |  | Microsoft Excel
6 | Complete top Level Use Case Diagram | 4 Days | 2021-02-16 | 2021-02-20 |  |  | Visual Paradigm
7 | Complete top Level Conceptual Class Diagram | 5 Days | 2021-02-20 | 2021-02-25 |  |  | Visual Paradigm
8 | Create Inception Planning Document | 4 Days | 2021-02-25 | 2021-03-01 |  |  | Microsoft Word
9 | Submit Inception Planning Document | 0 Days | 2021-03-01 | 2021-03-01 | Inception Planning Document | x
10 | Submit Use case Diagram | 0 Days | 2021-03-01 | 2021-03-01 | Top Level Use Case Diagram | x
11 | Submit Class Diagram | 0 Days | 2021-03-01 | 2021-03-01 | Top Level Conceptual Class Diagram | x
12 | Discussion with the client advising which part of the system to take forward | 0 Days | < 01/03/2021 | < 01/03/2021 |  | x
| Design Stage | 19 Days | 2021-03-02 | 2021-03-26
13 | Complete final top Level Use Case Diagram | 3 Days | 2021-03-02 | 2021-03-05 |  |  | Visual Paradigm
14 | Use Case Descriptions | 3 Days | 2021-03-06 | 2021-03-09 |  |  | Miscrosoft Word
15 | Activity Diagram | 3 Days | 2021-03-10 | 2021-03-13 |  |  | Visual Paradigm
16 | Sequence Diagram | 3 Days | 2021-03-14 | 2021-03-17 |  |  | Visual Paradigm
17 | GUI designs | 5 Days | 2021-03-18 | 2021-03-23 |  |  | Balsamiq Mockups 3
18 | Solution Planning Document | 2 Days | 2021-03-24 | 2021-03-26 |  |  | Miscrosoft Word
19 | Submit Solution Planning Document | 0 Days | 2021-03-26 | 2021-03-26 | Solution Planning Document | x
| Implementation Stage | 52 Days | 2021-03-27 | 2021-05-21
20 | Implementation | 40 Days | 2021-03-27 | 2021-05-06 |  |  | Eclipse
21 | Submit Working Application | 0 Days | 2021-05-06 | 2021-05-06 | Working Application | x
22 | Create Testing Documentation | 0 Days | 2021-05-07 | 2021-05-07 |  |  | Miscrosoft Word
23 | Testing | 4 Days | 2021-05-07 | 2021-05-11 |  |  | Miscrosoft Word
24 | Submit Testing Documentation | 0 Days | 2021-05-11 | 2021-05-11 | Testing Documentation | x
25 | Create User Documentation | 4 days | 2021-05-12 | 2021-05-16 |  |  | Miscrosoft Word
26 | Submit User Doucmentation | 0 Days | 2021-05-16 | 2021-05-16 | Application Documentation | x
27 | Submit Portfolio of Evidence | 4 Days | 2021-05-17 | 2021-05-21 | Portfolio | x | Miscrosoft Word
| Evaluation Stage | 5 Days | 2021-05-22 | 2021-05-27
28 | Evaluation | 5 Days | 2021-05-22 | 2021-05-27 |  |  | Miscrosoft Word
29 | Submit Evaluation | 0 Days | 2021-05-27 | 2021-05-27 | Evaluation Report | x